## Sheet1
Summary
| TTK8 Project |  |  |  | Obstacle detection with a nicla vision camera
Total planned (h) | Total used (h) | Total completion (%)
116 | 100 | 98%
| Semester Project |  | Info | This is a work breakdown structure for the semester project of fall 2025
Total planned (h) | Total used (h) | Total completion (%) | Goal | The objective of this project is to implement a nicla vision camera on a robot, to detect the distance and width of the closest obstacle.
300 | 143 | 56.65% | Student | Rebekka Alve
|  | Work Breakdown Structure (WBS) | [7 empty] | Plan of Progress (PoP)
[6 empty] | Colors : | Completed, Started, Unifinished after deadline, Planned
| Main Task | Subtasks | Planned Effort (h) | Real Effort (h) | Completion (%) | WEEK | 35-39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49
0 | Planning |  | 12 | 22 | 100% | Hours a week | 13.2 | 12 | 17 | 21 | 4 | 0 | 12 | 11
0.1 |  | Decide IDE, programming environment | 8 | 16 | 100% |  | 16
0.2 |  | create wbs, structure analysis | 4 | 6 | 100% |  | 6
1 | Setup & Environment |  | 12 | 10 | 100%
1.1 |  | Install drivers, libraries, test Nicla Vision | 8 | 8 | 100% |  | 8
1.2 |  | Setup ToF distance sensor | 4 | 2 | 100% |  | 2
2 | Basic Camera Functions |  | 28 | 17 | 100%
2.1 |  | Enable live stream over wifi | 8 | 10 | 100% |  | 6 | 1 | 1 | 1 | 1
2.2 |  | Capture & save frames | 4 | 3 | 100% |  | 1 |  |  | 2
2.3 |  | Preprocessing (grayscale, filtering) | 16 | 4 | 100% |  | 3 |  |  | 1
3 | Object Detection |  | 40 | 17 | 100%
3.1 |  | Implement simple detection (shapes/blobs) | 16 | 8 | 100% |  | 8
3.2 |  | Advanced tuning for robustness | 24 | 9 | 100% |  | 8 |  |  | 1
4 | Documentation camera code |  | 24 | 34 | 90%
4.1 |  | Testing and diagrams | 8 | 11 | 90% |  |  | 6 |  |  |  |  | 2 | 3
4.2 |  | Written documentation | 16 | 23 | 90% |  |  | 2 |  |  | 3 |  | 10 | 8 |  | Margin
|  | --- TTK8 Ends Here --- | [13 empty] | In case of bad planning
5 | Robot & Camera Integration |  | 32 | 41 | 75%
5.1 |  | Format obstacle info and send to robot | 16 | 16 | 80% |  | 8 |  | 8
5.2 |  | Connect camera to robot via uart | 16 | 25 | 70% |  |  | 1 | 8 | 16
6 | Server & Camera Integration |  | 24 | 0 | 0%
6.1 |  | Send results from robot to server | 16 | 0 | 0%
6.2 |  | Process and interpret obstacle info | 8 | 0 | 0%
7 | Obstacle mapping |  | 24 | 0 | 0%
7.1 |  | Add obstacles to map | 8 | 0 | 0%
7.2 |  | Use obstacle info to control robot | 16 | 0 | 0%
8 | Testing & Evaluation |  | 24 | 0 | 0%
8.1 |  | Indoor test with objects | 8 | 0 | 0%
8.2 |  | Optitrack testing with objects | 16 | 0 | 0%
9 | Documentation |  | 80 | 2 | 1.5%
9.1 |  | Structured analysis & diagrams | 24 | 0 | 0%
9.2 |  | Write user manual and project thesis | 56 | 2 | 3% |  |  | 2
Dependecies are linear
Next task depends on prior