## Sheet1
Summary
| TTK8 Project |  |  |  | Obstacle detection with a nicla vision camera
Total planned (h) | Total used (h) | Total completion (%)
116 | 63 | 76.33%
| Semester Project |  | Info | This is a work breakdown structure for the semester project of fall 2025
Total planned (h) | Total used (h) | Total completion (%) | Goal | The objective of this project is to implement a nicla vision camera on a robot, to detect the distance and width of the closest obstacle.
300 | 71 | 39.67% | Student | Rebekka Alve
|  | Work Breakdown Structure (WBS) | [7 empty] | Plan of Progress (PoP)
[6 empty] | Colors : | Completed, Started, Unifinished after deadline, Planned
| Main Task | Subtasks | Planned Effort (h) | Real Effort (h) | Completion (%) | WEEK | 34-39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49
0 | Planning |  | 12 | 22 | 100% | Hours a week | 11 | 5
0.1 |  | Decide IDE, programming environment | 8 | 16 | 100% |  | 16
0.2 |  | create wbs, structure analysis | 4 | 6 | 100% |  | 6
1 | Setup & Environment |  | 12 | 10 | 100%
1.1 |  | Install drivers, libraries, test Nicla Vision | 8 | 8 | 100% |  | 8
1.2 |  | Setup ToF distance sensor | 4 | 2 | 100% |  | 2
2 | Basic Camera Functions |  | 28 | 11 | 86.67%
2.1 |  | Enable live stream over wifi | 8 | 7 | 100% |  | 6 | 1
2.2 |  | Capture & save frames | 4 | 1 | 90% |  | 1
2.3 |  | Preprocessing (grayscale, filtering) | 16 | 3 | 70% |  | 3
3 | Object Detection |  | 40 | 16 | 70%
3.1 |  | Implement simple detection (shapes/blobs) | 16 | 8 | 100% |  | 8
3.2 |  | Advanced tuning for robustness | 24 | 8 | 40% |  | 8
4 | Documentation camera code |  | 24 | 4 | 25%
4.1 |  | Testing and diagrams | 8 | 4 | 50% |  |  | 4
4.2 |  | Written documentation | 16 | 0 | 0% |  |  | 0 | [7 empty] | Margin
|  | --- TTK8 Ends Here --- | [13 empty] | In case of bad planning
5 | Robot & Camera Integration |  | 32 | 8 | 15%
5.1 |  | Format obstacle info and send to robot | 16 | 8 | 30% |  | 8 | 0
5.2 |  | Connect camera to robot via ic/spi | 16 | 0 | 0%
6 | Server & Camera Integration |  | 24 | 0 | 0%
6.1 |  | Process and interpret obstacle info | 16 | 0 | 0% |  |  | 0
6.2 |  | Send results from robot to server | 8 | 0 | 0%
7 | Obstacle mapping |  | 24 | 0 | 0%
7.1 |  | Add obstacles to map | 8 | 0 | 0%
7.2 |  | Use obstacle info to control robot | 16 | 0 | 0%
8 | Testing & Evaluation |  | 24 | 0 | 0%
8.1 |  | Indoor test with objects | 8 | 0 | 0%
8.2 |  | Optitrack testing with objects | 16 | 0 | 0%
9 | Documentation |  | 80 | 0 | 0%
9.1 |  | Structured analysis & diagrams | 24 | 0 | 0%
9.2 |  | Write user manual and project thesis | 56 | 0 | 0%
Dependecies are linear
From 0 to 9